## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US 1 | Research image tampering techniques | MUST HAVE | None | Sandhiya R | 3- Completed
Sprint 1 | Sprint 1 | US 2 | Analyze dataset (CASIA) | MUST HAVE | US 1 | Sandhiya R | 3- Completed
Sprint 1 | Sprint 1 | US 3 | Finalize Resnet50 approach | MUST HAVE | US 2 | Sandhiya R | 3- Completed
Sprint 2 | Sprint 2 | US 4 | Load Dataset | MUST HAVE | US 3 | Sandhiya R | 3- Completed
Sprint 2 | Sprint 2 | US 5 | Clean & normalize dataset | MUST HAVE | US 4 | Sandhiya R | 3- Completed
Sprint 2 | Sprint 2 | US 6 | Split dataset | MUST HAVE | US 5 | Sandhiya R | 3- Completed
Sprint 3 | Sprint 3 | US 7 | Design resnet50 model | MUST HAVE | US 6 | Sandhiya R | 3- Completed
Sprint 3 | Sprint 3 | US 8 | Train model | MUST HAVE | US 7 | Sandhiya R | 3- Completed
Sprint 3 | Sprint 3 | US 9 | Evaluate model | MUST HAVE | US 8 | Sandhiya R | 3- Completed
Sprint 1 | Sprint 1 | US1 | As a developer, I want to download and organize the SROIE dataset so that I can train and test the address detection system. | MUST HAVE | None | Maheswari | 3- Completed
Sprint 1 | Sprint 1 | US 2 | As a developer, I need to load the dataset and use it for further process in the project. | MUST HAVE | US 1 | Maheswari | 3- Completed
Sprint 1 | Sprint 1 | US 3 | As a developer, I want to apply image preprocessing techniques such as resizing, grayscale conversion, and noise removal so that text detection accuracy improves. | MUST HAVE | US 2 | Maheswari | 3- Completed
Sprint 2 | Sprint 2 | US 4 | As a developer, I want to train a YOLO model using annotated SROIE images so that text regions in documents can be detected automatically. | MUST HAVE | US 3 | Bhargavi K | 3- Completed
Sprint 2 | Sprint 2 | US 5 | As a developer, I want to integrate EasyOCR to extract text from detected regions so that address information can be obtained from images. | MUST HAVE | US 4 | Bhargavi K | 3- Completed
Sprint 3 | Sprint 3 | US 6 | As a system, I want to identify and extract address-related text from OCR output so that only relevant address information is retained. | MUST HAVE | US 5 | Bhargavi K | 3- Completed
Sprint 3 | Sprint 3 | US 7 | As a user, I want the extracted address to be displayed on screen so that I can verify the information.As a user, I want the extracted address to be displayed and saved so that I can verify and reuse the detected information. | SHOULD HAVE | US 6 | Bhargavi K | 3- Completed
Sprint 1 | Sprint 1 | US 1 | Collect and organize selfie and ID image dataset | MUST HAVE | None | Deeksha H L | 3- Completed
Sprint 1 | Sprint 1 | US 2 | Preprocess images – resize, normalize, augment | MUST HAVE | US 1 | Deeksha H L | 3- Completed
Sprint 2 | Sprint 2 | US 3 | Extract face embeddings using pretrained FaceNet | MUST HAVE | US 2 | Pravalli l | 3- Completed
Sprint 2 | Sprint 2 | US 4 | Compute cosine similarity and L2 distance between pairs | MUST HAVE | US 3 | Pravalli l | 3- Completed
Sprint 2 | Sprint 2 | US 5 | Implement ensemble similarity approach (cosine + L2) | SHOULD HAVE | US 4 | Pravalli l | 3- Completed
Sprint 3 | Sprint 3 | US 6 | Perform hard negative mining on impostor pairs | SHOULD HAVE | US 5 | Pravalli l | 3- Completed
Sprint 3 | Sprint 3 | US 7 | Select optimal threshold using ROC and Youden's Index | MUST HAVE | US 6 | Devi Pragada | 3- Completed
Sprint 4 | Sprint 4 | US 8 | Evaluate model using Accuracy, F1, AUC, FAR, FRR | MUST HAVE | US 7 | Devi Pragada | 3- Completed
Sprint 4 | Sprint 4 | US 9 | Train Logistic Regression and compare with similarity method | COULD HAVE | US 8 | Devi Pragada | 3- Completed
Sprint 4 | Sprint 4 | US I0 | Save embeddings, results, and evaluation plots | MUST HAVE | US 9 | Deeksha H L | 3- Completed
Sprint 5 | Sprint 5 | US 1 | As a user, I want to upload ID documents for verification | MUST HAVE | US 1 | Fariyal Jamadar | 3- Completed
Sprint 5 | Sprint 5 | US 2 | As a system, I want to extract data using OCR | MUST HAVE | US 2 | Fariyal Jamadar | 3- Completed
Sprint 5 | Sprint 5 | US 3 | As a system, I want to match face with ID photo | MUST HAVE | US 3 | Fariyal Jamadar | 3- Completed
Sprint 5 | Sprint 5 | US 4 | As a system, I want to detect fake/forged documents | MUST HAVE | US 4 | Fariyal Jamadar | 3- Completed
Sprint 5 | Sprint 5 | US 5 | As a system, I want to detect fake/forged documents | MUST HAVE | US 5 | Fariyal Jamadar | 3- Completed
Sprint 5 | Sprint 5 | US 6 | As admin, I want dashboard for monitoring | MUST HAVE | US 6 | Fariyal Jamadar | 3- Completed
Sprint 1 | Sprint 1 | US 1 | As a developer, I want to set up project structure and HTML framework so that frontend foundation is ready. | MUST HAVE | US1 | Siddineni Gopala Krishna | 3- Completed
Sprint 1 | Sprint 1 | US 2 | As a developer, I want to create CSS variables and framework for consistent theming across all pages. | MUST HAVE | US2 | Siddineni Gopala Krishna | 3- Completed
Sprint 1 | Sprint 1 | US 3 | As a user, I want to see a login page so that I can access the KYC verification system. | MUST HAVE | US3 | Siddineni Gopala Krishna | 3- Completed
Sprint 1 | Sprint 1 | US 4 | As a new user, I want to register with my details so that I can create an account. | MUST HAVE | US4 | Siddineni Gopala Krishna | 3- Completed
Sprint 2 | Sprint 2 | US 5 | As a user, I want to see dashboard with statistics cards to view verification metrics. | MUST HAVE | US5 | Siddineni Gopala Krishna | 3- Completed
Sprint 2 | Sprint 2 | US 6 | As a user, I want to see recent verifications table to track KYC applications. | MUST HAVE | US6 | Siddineni Gopala Krishna | 3- Completed
Sprint 2 | Sprint 2 | US 7 | As a user, I want risk case review section with action buttons to manage flagged cases. | MUST HAVE | US7 | Siddineni Gopala Krishna | 3- Completed
Sprint 2 | Sprint 2 | US 8 | As a user, I want to see AI verification results to view face match and document scores. | SHOULD HAVE | US8 | Siddineni Gopala Krishna | 3- Completed
Sprint 3 | Sprint 3 | US 9 | As a user, I want verifications page with search and filter options to find specific records | MUST HAVE | US9 | Siddineni Gopala Krishna | 3- Completed
Sprint 3 | Sprint 3 | US 10 | As a user, I want flagged alerts page to monitor fraud risks | MUST HAVE | US10 | Siddineni Gopala Krishna | 3- Completed
Sprint 3 | Sprint 3 | US 11 | As a user, I want to upload documents to submit identity proofs for verification | MUST HAVE | US11 | Siddineni Gopala Krishna | 3- Completed
Sprint 3 | Sprint 3 | US 12 | As a user, I want to view recent documents to track uploaded files | SHOULD HAVE | US12 | Siddineni Gopala Krishna | 3- Completed
Sprint 4 | Sprint 4 | US 13 | As a user, I want analytics dashboard with charts to see verification trends | MUST HAVE | US13 | Siddineni Gopala Krishna | 3- Completed
Sprint 4 | Sprint 4 | US 14 | As a user, I want to customize settings (dark mode, notifications) for personalization | SHOULD HAVE | US14 | Siddineni Gopala Krishna | 3- Completed
Sprint 4 | Sprint 4 | US 15 | As a user, I want to edit my profile to update personal information. | MUST HAVE | US15 | Siddineni Gopala Krishna | 3- Completed
Sprint 5 | Sprint 5 | US 16 | As a user, I want responsive interface for mobile and tablet access | COULD HAVE | US16 | Siddineni Gopala Krishna | 3- Completed
Sprint 5 | Sprint 5 | US 17 | As a user, I want smooth animations on buttons and cards for interactive UI | SHOULD HAVE | US17 | Siddineni Gopala Krishna | 3- Completed
Sprint 5 | Sprint 5 | US 18 | As a developer, I want dark mode with localStorage so that preferences are saved
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 147 | 18 | 19 | 4 | 7 | 8 | 7 | 6 | 18 | 12 | 12 | 7 | 6 | 9 | 16
SPRINT 1 BACKLOG
US1 | T1 | Research & paper review | Day 1 | Day 2 | Sandhiya R | Design | 3- Completed | 7 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US2 | T2 | Dataset analysis & loading | Day 2 | Day 4 | Sandhiya R | Coding | 3- Completed | 4 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US3 | T3 | Data preprocessing (clean + resize + split) | Day 5 | Day 7 | Sandhiya R | Coding | 3- Completed | 9 | 0 | 0 | 0 | 0 | 3 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US4 | T4 | Model design & training | Day 8 | Day 11 | Sandhiya R | Build | 3- Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 2 | 2 | 0 | 0 | 0
US 5 | T5 | Evaluation & tuning | Day 12 | Day 14 | Sandhiya R | System Test | 3- Completed | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 0
US1 | T1 | Download SROIE dataset from official source | Day 1 | Day 2 | Maheshwari | Coding | 3- Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US1 | T2 | Extract dataset and verify image and annotation files | Day 3 | Day 3 | Maheshwari | Coding | 3- Completed | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US2 | T3 | Load dataset into Python environment for processing | Day 4 | Day 4 | Maheshwari | Coding | 3- Completed | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US3 | T4 | Implement image resizing for all dataset images | Day 5 | Day 5 | Maheshwari | Coding | 3- Completed | 3 | 0 | 0 | 0 | 0 | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US3 | T5 | Apply grayscale conversion and noise removal | Day 6 | Day 6 | Maheshwari | Coding | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US4 | T6 | Configure YOLO training environment and dependencies | Day 7 | Day 7 | Bhargavi K | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US4 | T7 | Train YOLO model using annotated SROIE images | Day 8 | Day 10 | Bhargavi K | Coding | 3- Completed | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 0
US 5 | T8 | Install and configure EasyOCR library | Day 11 | Day 11 | Bhargavi K | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
US 5 | T9 | Extract text from YOLO-detected regions using EasyOCR | Day 12 | Day 12 | Bhargavi K | Coding | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0
US 6 | T10 | Implement logic to identify address text from OCR output | Day 13 | Day 13 | Bhargavi K | Coding | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
US 7 | T11 | Display extracted address on screen for verification | Day 14 | Day 14 | Bhargavi K | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
US 7 | T12 | Save extracted address to output file for reuse | Day 14 | Day 14 | Bhargavi K | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US1 | F1 | Project Setup & HTML Structure | Day 1 | Day 1 | Siddineni Gopala Krishna | Coding | 3- Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US1 | F2 | CSS Framework Setup & Variables | Day 1 | Day 2 | Siddineni Gopala Krishna | Design | 3- Completed | 3 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US2 | F3 | Login Page UI Design | Day 2 | Day 2 | Siddineni Gopala Krishna | UI/UX | 3- Completed | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US2 | F4 | Register Form UI Design | Day 2 | Day 3 | Siddineni Gopala Krishna | UI/UX | 3- Completed | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US3 | F5 | Sidebar Navigation Component | Day 3 | Day 3 | Siddineni Gopala Krishna | Coding | 3- Completed | 4 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US3 | F6 | Dashboard Stats Cards Ul | Day 3 | Day 4 | Siddineni Gopala Krishna | Coding | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US4 | F7 | KYC Table Design & Layout | Day 4 | Day 4 | Siddineni Gopala Krishna | Coding | 3- Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US4 | F8 | Risk Case Review Buttons (6 Buttons) | Day 4 | Day 5 | Siddineni Gopala Krishna | UI/UX | 3- Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US5 | F9 | Al Verification Result Card | Day 5 | Day 5 | Siddineni Gopala Krishna | Coding | 3- Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US5 | F10 | Fraud Analysis Card | Day 5 | Day 5 | Siddineni Gopala Krishna | Coding | 3- Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US6 | F11 | Final Decision Card | Day 6 | Day 6 | Siddineni Gopala Krishna | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
US6 | F12 | Dashboard Footer (Search, Language, Date) | Day 6 | Day 6 | Siddineni Gopala Krishna | UI/UX | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0
US7 | F13 | Verifications Page Ul | Day 7 | Day 7 | Siddineni Gopala Krishna | Coding | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0
US7 | F14 | Search & Filter Functionality | Day 7 | Day 8 | Siddineni Gopala Krishna | Coding | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
US8 | F15 | Alerts Page UI & Table | Day 8 | Day 8 | Siddineni Gopala Krishna | Coding | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0
US8 | F16 | Risk Level Badges (High/Medium/Low) | Day 8 | Day 9 | Siddineni Gopala Krishna | UI/UX | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
US9 | F17 | Documents Page Ul | Day 9 | Day 9 | Siddineni Gopala Krishna | Coding | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0
US9 | F18 | Document Upload Cards (4 Types) | Day 9 | Day 10 | Siddineni Gopala Krishna | UI/UX | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0
US10 | F19 | Recent Documents Table | Day 10 | Day 10 | Siddineni Gopala Krishna | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
US11 | F20 | Analytics Page Ul | Day 11 | Day 11 | Siddineni Gopala Krishna | Coding | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
US12 | F21 | Settings Page UI & Tabs | Day 12 | Day 13 | Siddineni Gopala Krishna | Coding | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
US12 | F23 | Toggle Switches & Sliders | Day 13 | Day 13 | Siddineni Gopala Krishna | UI/UX | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
US13 | F24 | Profile Modal with Edit Functionality | Day 13 | Day 14 | Siddineni Gopala Krishna | Coding | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
US14 | F25 | Dark Mode Implementation | Day 14 | Day 14 | Siddineni Gopala Krishna | Coding | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Too many tampering detection techniques | reviewed multiple research papers and shortlisted methods
Sprint 1 | Day 2 | Difficulty understaning dataset differences | compared datasets and selected CASIA dataset
Sprint 1 | Day 3 | confusion in choosing model architecture | finalized resnet50 approach
Sprint 2 | Day 4 | dataset not loading properly | fixed file path and directory structure
Sprint 2 | Day 5 | dataset not loading properly | removed invalid images from dataset
Sprint 2 | Day 6 | dataset not loading properly | applied resizing to standard dimensions
Sprint 2 | Day 7 | data imbalance issue | adjusted dataset split properly
Sprint 3 | Day 8 | Difficulty designing model structure | implemented resnet50 architecture stepbystep
Sprint 3 | Day 9 | training taking too long | reduced batch size and optimized code
Sprint 3 | Day 10 | low model accuracy | tuned hyperparameters
Sprint 3 | Day 11 | overfitting problem | added dropout layers
Sprint 1 | Day 1 | HTML structure not loading properly | Created proper folder structure and linked all CSS/JS files correctly
Sprint 1 | Day 1 | HTML structure not loading properly | Created proper folder structure and linked all CSS/JS files correctly
Sprint 1 | Day 2 | CSS framework integration issues | Set up CSS variables and global styles for consistent theming
Sprint 1 | Day 3 | Login page Ul alignment issues | Fixed flexbox and grid layouts for responsive design
Sprint 1 | Day 4 | Register form fields not validating | Implemented JavaScript validation for all form fields
Sprint 1 | Day 5 | Sidebar navigation not working | Fixed href links and active state styling
Sprint 2 | Day 6 | Dashboard stats cards not displaying | Fixed data binding from JavaScript to HTML elements
Sprint 2 | Day 7 | KYC table data not loading | Corrected data array structure and dynamic table generation
Sprint 2 | Day 8 | 6 risk buttons not aligning properly | Implemented CSS grid with 3x2 layout for proper alignment
Sprint 2 | Day 9 | Al verification cards layout broken | Fixed card styling and responsive grid layout
Sprint 2 | Day 10 | Fraud analysis section not showing | Debugged HTML structure and CSS display properties
Sprint 3 | Day 11 | Dark mode toggle not working | Added localStorage persistence and toggle functionality
Sprint 3 | Day 12 | Profile modal not opening | Fixed modal display CSS and JavaScript click events
Sprint 3 | Day 13 | Analytics charts not loading | Integrated Chart.js library and initialized charts on window load
Sprint 3 | Day 14 | Document upload page navigation issue | Fixed sidebar active state and href links
Sprint 3

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | Day 1 | Day 3 | Sandhiya R | Validate approach before implementation | Randomly exploringwithout direction | Documenting research finding | Finalized Resnet50 approach and dataset
2 | Sprint 2 | Day 4 | Day 7 | Sandhiya R | Check data quality before processing | Ignoring corrupted data | Breaking tasks into smaller steps | Cleaned dataset and standardized images
3 | Sprint 3 | day 8 | Day 14 | Sandhiya R | Test model on small data before full training | Running full training without validation | Monitoring accuracy and loss | Improved model performance using tuning
4 | Sprint 1 | Day 1 | Day 6 | Bhargavi K Maheshwari S | Analyze problem and select correct model approach | Randomly choosing methods without analysis | Researching different techniques | Finalized YOLOv8 and EasyOCR approach
5 | Sprint 2 | Day 7 | Day 13 | Maheswari S | Validate and clean dataset before processing | Ignoring corrupted or missing data | Organizing dataset properly | Cleaned dataset and fixed file structure
6 | Sprint 3 | Day 14 | Day 14 | Bhargavi K | Train model with validation | Running training without monitoring performance | Tracking accuracy and loss | Improved model using increasing ephocs
7 | Sprint 1 | Day 1 | Day 3 | Siddineni Gopala Krishna | Plan HTML structure before coding | Avoid starting coding without layout planning | Follow design mockups | Created folder structure and HTML skeleton
8 | Sprint 1 | Day 2 | Day 4 | Siddineni Gopala Krishna | Use CSS variables for theming | Avoid hardcoding colors and values | Use reusable CSS classes | Set up global CSS variables and framework
9 | Sprint 2 | Day 5 | Day 7 | Siddineni Gopala Krishna | Test responsive design | Avoid ignoring mobile view | Check layout after each change | Fixed flexbox and grid responsiveness
10 | Sprint 2 | Day 8 | Day 10 | Siddineni Gopala Krishna | Validate JavaScript functionality | Avoid writing code without testing | Test each function | Implemented and tested all features
11 | Sprint 3 | Day 11 | Day 13 | Siddineni Gopala Krishna | Use localStorage for data | Avoid storing data only in memory | Save user preferences | Implemented localStorage for dark mode and user data
12 | Sprint 3 | Day 14 | Day 15 | Siddineni Gopala Krishna | Add CSS animations | Avoid static UI | Improve user experience | Added shimmer, pulse, and hover animations